## Sheet1
To Do List
Physical Part | In Charge | Status | Details
Faceplate | Scooter | Complete
Housing | Juan | Pending | Needs assembly and master cylinder cover
Hall Effect Sensors | Scooter | Pending | Waiting on new shipment
Hall Effect Brackets | Scooter | Complete
Temperature Sensor | Krystal | Complete
Fan | Krystal | Complete
Voltage Sensor | Krystal | Complete
Switches | Scooter | Complete
Servos | Krystal | Complete
Buttons | Krystal | Complete
LCD | Krystal | Complete
Real Time Clock | Krystal | Complete
SD Card | Krystal | Complete
LEDs | Krystal | Complete
Custom Shield | Sidra | Complete
Shield Bracket | Christian | Not Started | Need new design and 3D print
Battery | Everyone | Complete
Battery Management System |  | Pending | Needs testing with battery charger
Battery Charger |  | Pending | Needs testing with battery
Wiring Harness | Everyone | Pending | Needs testing with EVERYTHING installed; resolder SW.1 connector
Wheatstone Bridge | Krystal | Complete
Load Cell |  | Complete
Dash Mounting Tabs | Juan/Sosa | Pending | In production/need to be welded on to frame
Electrical Connectors | Everyone | Pending | Needs final verification and add as needed; hot glue any loose connections
Programming To-Do List | Function | Status | Details
Switch 1 | Main Power | Complete
Switch 2 | AUX | N/A
Servo 1 | Speed | Complete
Servo 2 | CVT Ratio | Complete
Button 1 | Record | Pending | Start/Stop recording with every press
Button 2 | Cycle LCD | Pending | Cycle through FORCE, RPM, or whatever other data we could use on LCD
LED 1 | SD Detect | Pending | Needs to turn on when SD card is inserted
LED 2 | Record | Pending | Flash when recording, off when not recording
LED 3 | Low Battery Ind. | Pending | Flash rapidly when battery level is low
LED 4 | AUX | N/A
LED 5 | Ideal Ratio Ind. | Pending | Tentative; Luis wants to make this turn on when we are at or near a 1:1 ratio
LCD | Display | Complete
Hall Effect Sensors | RPM | Complete
Voltage Sensor | Low Battery | Pending | Send signal to LED 3 (low battery indicator)
Temperature Sensor | Fan | Complete
RTC | Data | Complete
SD Card | Data | Complete
Wheatstone Bridge/Load Cell | Data | Complete
Master Code | Data | Pending | Waiting on above